## Master Test Plan
Aioi App Automation & API Test Plan |  |  |  | Test Plan ID | AIOI-TP-2026.02
Introduction | Validating core user validation matrices, frontend conditional form toggles, and NZ Post API network integration layers within the Aioi ecosystem using custom validation frameworks. |  |  | Test Plan Author | QA Lead
|  |  |  | Date | 05/16/2026
Objectives | 1. Maintain 100% automated UI/API assertion coverage. 2. Verify granular, step-by-step missing-field error messaging on form submissions. 3. Ensure clean visual UI transitions during address-entry mode switches. |  |  | Test Management Tool | Playwright + GitHub Actions
|  |  |  | Progress Tracker | 0%
Scope | In-Scope: Playwright E2E testing, standalone and combination empty-state field tracking, state cleansing rules (removing search errors when entering manual mode), and mock API interception testing. Out-of-Scope: Standard browser tooltips (HTML5 default behavior) and live key production endpoints during mock phases.
Test Item | Test Strategy | Testing Types | Features to Be Tested | Features Not to Be Tested | Entry Criteria | Exit Criteria | Deliverables | Dependencies | Start Date | End Date | Assignee | KPIs | Risk & Mitigation Plan | Sign-Off
Login Authentication – Missing State Validation Waterfall | Playwright script-driven boundary/empty entry checks to mimic button clicks. | Functional UI, Edge-case validation | Submitting with both inputs empty renders separate custom "Please enter email" and "Please enter password" text blocks; entering email only isolates the password error; entering password only isolates the email error; typing inside a flagged input instantly clears its error text and red border. | Browser native HTML5 tooltip validation bubbles. | Login page accessible at /login route; noValidate attribute present on <form>. | Form uses the noValidate parent property so native browser bubbles are suppressed in favor of custom UI rendering. | tests/auth-validation.spec.js automated script. | Playwright test runner configured; dev server running. | 05/16/2026 |  | QA Lead | 100% field-level error coverage | High Risk: Browser native tooltips block UI assertions. Mitigation: Enforce noValidate checks on the main form context element.
Login Authentication – Credentials Matching | Hardcoded credential matching verification. | Functional UI, Boundary testing | Input string validation against admin@test.com and Admin123; boundary error messaging for incorrect credentials; redirect route matching to the Address Checker interface upon successful login. | Password strength enforcement; account lockout policies. | Login page loaded with valid form elements. | Successful login redirects to "/" dashboard; failed login displays inline error message. | tests/auth-credentials.spec.js automated spec file. | Hardcoded credentials configured in login handler. | 05/16/2026 |  | QA Lead | 100% credential path coverage | Low Risk: Hardcoded credentials may change. Mitigation: Centralise credential constants for single-point updates.
Address Checker – Mode Swapping & State Cleansing | Functional Playwright visibility assertions during link clicks. | Interaction, Usability | Clicking "enter here manually" exposes the hidden Street, Suburb, City, and Postcode fields; clicking this mode switch instantly purges/nullifies any preexisting "No matching address found" validation message from the screen view. | Styling/pixel-level CSS validation of form fields. | User authenticated and on the Address Checker page. | Verification that the legacy address search error state cannot linger in the viewport once manual mode is active. | tests/address-toggle.spec.js automated interaction spec. | Authentication flow passing; address search API route available. | 05/16/2026 |  | QA Lead | 100% mode-switch state assertions | Medium Risk: Timing issues with state transitions. Mitigation: Use Playwright auto-waiting and explicit waitFor assertions.
NZ Post Autocomplete Address API Endpoint | Network interception using Playwright's page.route() router to simulate varying server responses. | API Integration, Mock Fallback Verification | Successful query parameter formatting; data-mapping arrays from a simulated 200 OK block; automatic graceful fallback trigger opening manual address forms instantly when a 500 Internal Server Error is intercepted. | Live NZ Post production endpoint availability; real API key validation. | API route /api/address operational; Playwright route interception configured. | All mock response scenarios (200, 500, empty results) handled gracefully with correct UI state transitions. | tests/nz-post-api.spec.js paired with mock fixture assets. | Valid locally loaded .env.local variable parsing configuration. | 05/16/2026 |  | QA Lead | 100% API response path coverage | High Risk: Real API contract may differ from mock structure. Mitigation: Maintain a living fixture schema file; run contract tests once real keys are available.